Justification for selection and engagement of Project Management Unit (PMU) under_FMR-

Background for engagement

Public Health and Family Welfare Department, Government of Madhya Pradesh has planned to undertake several health systems strengthening initiatives in the next few years through its entities National Health Mission, Madhya Pradesh Public Health Services Corporation Limited. The various health programs and initiatives currently implemented in the state have resulted significantly in improving health indicators, however the department intends to further strengthen and integrate the implementation of national and state health programs and initiatives. The department initially wants to focus on strengthening operations and implementation of various projects under NHM-MP, Madhya Pradesh Public Health Services Corporation Limited (MPPHSCL) and NIRAMAYAM.

In lieu of the envisaged vision to improve the healthcare scenario of the state, NHM-MP has engaged a reputed consultancy organization in form of a Project Management Unit (PMU) to provide technical support in the implementation and monitoring of various ongoing/ new initiatives/ projects through MP National Health Mission. The main objective of the assignment is to advise and assist the Authority on the current functioning and newly planned initiatives to be rolled-out across the state.

NHM-MP has engaged the PMU as there is limited band-width within the organization to effectively and efficiently manage the above-mentioned envisaged services. The engaged PMU has been dedicatedly handling these services and provides expert Technical inputs to further strengthen the scheme wherever feasible. The engaged PMU would also enable NHM-MP in providing an unbiased perspective wrt to various initiatives/ activities being rolled-out and conduct continuous assessment and monitoring evaluation of the same on an on-going basis.

The envisaged scope of work being handled by the engaged PMU agency is as mentioned below. However, the same would not be limited and agency would have to carry out any of the allocated tasks as directed by NHM-MP. The brief scope of work wrt to this engagement would be as follows:

  - Transaction Advisory for health projects

  - The PMU shall assist the Authority in PPP/outsourcing advisory

  - PPP/Project Structuring

  - Preparation of Bidding documents and assistance in bid process

    - RFQ/ Qualification criteria

    - Concession Agreement

    - Non – Technical Schedules

    - Conduct Bid Process

    - Investor outreach

    - Pre-bid conference

    - Assistance in technical bid evaluation

    - Assistance in financial bid evaluation

    - Assistance in finalization of Letter of award

    - Assistance in finalization of concession agreement

    - Assistance in achieving financial closure (only Authority’s conditions precedents)

  - Post Transaction Monitoring support

- Provide handholding support to the Authority for contract monitoring

- Monitoring of Condition Precedence, review of performance indicators etc.

- Assessment of milestones, progress and adherence to timelines

- Listing specific tasks and operational procedures to help in supervision and contract management on day to day basis

- Coordinating between Government and Private agencies

- Follow with Authority (NHM) for fulfillment of obligations, providing list of   pending approvals

- Follow up with private agencies for fulfillment of obligations and condition precedents etc.

- Compliance with the instructions of the project authority or Independent expert as the case may be

  - Miscellaneous

  - Levy of user charges in accordance with the Terms of the concession agreement

  - Assist the Authority in identifying events of imposing penalties / liquidated damages for non-adherence of KPIs

  - Develop a framework for concession monitoring

  - Preparation of format for monthly report for each project. The format should be carefully prepared to include all the obligations of the private partner and the Authority, as specified in the agreement. It should serve as a check-list for ensuring that the provisions of the agreement are being complied with

  - Prepare monthly ‘Compliance Report’ regarding implementation of the various healthcare PPP / outsourcing projects as per the provisions of the respective contracts including compliance of conditions, adherence to timelines, assessment of performance, remedial measures, imposition of penalties, etc.

  - Prepare an ‘Exception Report’ highlighting issues where remedial action is to be taken for enforcing the provisions of the respective contracts

  - Conduct review for all Contracts as per timelines defined in the individual service agreements and submit review reports to the Nodal Authority

  - Assist the Nodal Authority in organizing and conducting regular meetings to discuss project progress

- Coordinate between Nodal Authority, private partner and other departments under the Nodal Authority for fulfilment of obligations, pending approvals/ conditions precedent etc.

- Assist the Nodal Authority in identifying events of imposing penalties / liquidated damages for non-adherence of KPIs/ milestones

- Ensure documentation of all the meetings, reports, discussions, payments and any other activities for facilitating communication between Private Partners and the Nodal and/or Payment Authority. The communication system between PMU and the Nodal Authority should be robust and transparent to capture and retain all the correspondence.

- Technical / legal vetting of MOU’s entered into between Public Health and Family Welfare Department, Government of Madhya Pradesh and different development partner agencies.

- Technical / legal vetting of MOU’s entered into between Public Health and Family Welfare Department, Government of Madhya Pradesh and different development partner agencies

Moreover, there has been a dedicated team of resources within PMU team who have been designated for monitoring and evaluation of Referral Transport Management Services. The scope of work for management of referral services to be carried out is as follows:

- Study RFP/ Service Level Agreement (SLA) related to integrated Referral Transport Management (RTM) system like 108, 104, Janani and Mobile medical units (MMUS).

- Develop understanding of SLAs and required operations and performance of the integrated referral transport system.

- Study the entire Referral Transport Management System which includes

    - Current software being used and its functionalities

    - Referral Transport planning and fleet management

    - HR planning, training & deployment

    - SOPs/ Manual

    - On ground operations planning and management of Referral Transport

    - Complete call life cycle management

    - Performance monitoring system

    - Customer feedback and grievance redressal management system

    - Disaster Management plan/ emergency response plan

    - Data management and recovery system

- Identify any gaps with respect to current operations and performance and SLA.

- Study and develop a frameworks and procedures for conducting periodic (monthly/ bi-monthly/ quarterly) assessment of operation, performance and other key indicators as per the Service Level Agreement/ Contract signed between the Authority and Service Provider(s).

- Undertake periodic (i.e. monthly/ bi-monthly/ quarterly) assessment for defined parameters at RTM call center level and data analysis.

- Prepare and submit SLA monitoring report to the Authority.

- Basis on the periodic assessment of work carried out by SP and analysis of bill of material/ invoices submitted by the service provider(s) to assess the payment computation & penalties as per the SLA.

- Provide recommendation for continuous improvement in operations and performance of RTM.

- Assess and recommend the required support system at the Authority level to take over the entire operations management of RTM in case of any eventuality resulting in termination of contract between the service provider(s) and the Authority

Proposed financials for engagement of PMU

The PMU team comprises of a dedicated 12-15 resources to carry out the above-mentioned scope of work and services within the same, the resource positions are as follows:

  - Team Lead – Public Health

  - Medical Expert

  - Legal Expert

  - Supply Chain and Procurement Consultant

  - Contract and Bid Documentation Expert

  - Bio-medical Engineering Consultant

  - IT System Consultant

  - Finance Expert

  - Consultant – Public Health Contract Management

  - Consultant – IT

  - Consultant – Call Centre and Operations

  - Consultant – Service Operation 108

  - Consultant – Service Operation Janani, MMUs

The overall payout on an annual basis for the above-mentioned dedicated resources would be ~3.6 Crores per annum. NHM-MP wishes to engage the PMU for a period of minimum 3 years in order to effectively utilize the services and thus in-turn help improve the overall healthcare scenario of the state by providing rigorous and continuous monitoring and evaluation of the services.

The break-up of proposed financial outlay per annum would be as follows:

| S. No. | Position as per ToR | Man-month rate | Annual payout |
| --- | --- | --- | --- |
| 1 | Team Leader – Public Health | 2,50,000 | 30,00,000 |
| 2 | Medical Expert | 2,50,000 | 30,00,000 |
| 3 | Legal Expert | 2,30,000 | 27,60,000 |
| 4 | Supply Chain and Procurement Consultant | 2,00,000 | 24,00,000 |
| 5 | Contract and Bid Documentation Expert | 2,00,000 | 24,00,000 |
| 6 | Bio-medical Engineering Consultant | 1,50,000 | 18,00,000 |
| 7 | IT System Consultant | 1,50,000 | 18,00,000 |
| 8 | Finance Expert | 1,70,000 | 20,40,000 |
| 9 | Consultant – Public Health Contract Management | 2,50,000 | 30,00,000/- |
| 10 | Consultant – IT | 1,50,000 | 18,00,000 |
| 11 | Consultant – Call Centre and Operations | 1,50,000 | 18,00,000 |
| 12 | Consultant – Service Operation 108 | 2,00,000 | 24,00,000 |
| 13 | Consultant – Service Operation Janani, MMUs | 2,00,000 | 24,00,000 |
| Total annual payout for PMU (excluding taxes) |  |  | 3,06,00,000/- |
| Applicable taxes (18%) |  |  | 55,08,000/- |
| Total annual payout for PMU (including taxes) |  |  | ~3,60,00,000/- |

Work done till date by engaged PMU

Till date the following mentioned activities have been initiated and completed by the engaged PMU. The following EOIs and RfPs have been developed by PMU till date:

- RfP for Selection of Manpower Recruitment Agency

- RfP for Selection of agency for providing Telemedicine services

- RfP for Selection of PPSA under RNTCP

- RfP for Selection of agency to provide IEC services

- RfP for Selection of agency to provide Concurrent audit services

- EOI for selection of agency to provide blood components separation services

- EOI for selection of agency to provide services for STEMI management

- EOI for selection of agency to provide Mental Health Counselling services

Of these developed EOIs & RfPs, 3 of the RfPs namely for Manpower Recruitment Agency, Telemedicine Services and PPSA services has been floated on MP e-portal. The remaining EOIs/ RfPs are under process for approval so that the same can be uploaded on portal for further processing.

Also, for Manpower Recruitment Agency RfP, the PMU effectively handled the Bid Process, successfully conducted the technical evaluation, presentation by eligible agency(s) and then conducted the financial evaluation also. The agency for this RfP had been selected and handed the Letter of Award (LOA) to accept the same initiate working within the next couple of weeks with NHM-MP.

In addition, PMU has also done the following additional tasks:

- As-Is assessment and mapping of current processes at MPPHSCL

- Conducting gap analysis for processes mapped at MPPHSCL

- Technical evaluation of tenders for Skilled and Un-skilled Manpower agency(s)

- Evaluation and population of checklist for personnel to be re-deployed with NHM-MP

- Study and assessment of current state of operations within the referral transport management services