IT initiatives

ACTIVITY 1:   Central Support Team for e-Vittapravaha (new activity)

I	BACKGROUND

National Health Mission (NHM) MP has developed a financial management and an online payment system which uses PFMS as a payment engine, as mandated by NHM, GoI. e-Vittapravaha facilitates implementation of single account banking concept by leveraging technology to ensure utilization of funds for planned programmatic health interventions as sanctioned in the PIP. The online application is used as a platform to devolve financial powers till block level and expedite payment processing through e sanctions using biometrics. e-Vittapravaha has been developed on a no cost basis to NHM. It is an application provided as a service by the partnering bank where the single account has been kept.

The main objectives of e-Vittapravaha include but are not limited to the following:

- to device a tool for quick dissemination of PIP

- limiting expenditure against a particular activity based on PIP sanctions

- consolidating and managing NHM’s funds

- ensuring better access of funds to all DDOs

- facilitating efficient payment mechanism

- reducing the practice of fragmented system of handling NHM payments

- facilitating a unified view, improved fund management and centralized control over NHM’s funds; avoiding the situation of unspent/ cash lying idle for extended periods in numerous accounts

- lastly monitoring of expenditure by DDOs against various programs.

e-Vittapravaha also has a separate module to handle the state specific scheme of Prasooti Sahayata Yojana, which is a state level direct benefit transfer scheme. This module is integrated with the partnering bank’s server for financial transactions. The application is hosted in the State Data Centre. As on date the application is being used by 446 DDOs and 1395 users.

II	IMPLEMENTATION CHALLENGES

e-Vittapravaha has several utilities which need to be constantly managed from the state office. The tasks include but are not confined to the following:

- mapping of masters

- deployment of new utilities

- database management

- handling users requirements

- biometrics

- user creation

- budget allocation

- user updation

All these tasks need to be handled by NHM. Fund flow being a critical issue, cannot be stalled and response time for issue resolving need to be very less.

III	JUSTIFICATION

e-Vittapravaha went live in August 2018 and till now was being maintained by the partnering bank and its technical partner. With the development phase drawing to a closure and the banking partner coming to the support phase coupled with the application becoming a real time payment portal, it is now required that all maintenance and support activities be owned and done under the supervision of NHM. The data of e-Vittapravaha is hosted at the State Data Centre. Typically, the efficiency of any financial management and payment online system is largely dependent on the accuracy of mapping of masters, management of Database, responding to users and their problems and responding to the evolutionary changes in the government processes. As of now, there is no dedicated team and structural systems in NHM to handle the application.

During the commencement of the project, the users were less and issues were minimal but with the maturity of the project and ever-increasing percolation of e-Vittapravaha, the requirement to have a dedicated team which is a part of NHM is increasing and needs to be urgently addressed. Therefore, in order to ensure complete control of NHM on the application, it is proposed to have a dedicated management team for e-Vittapravaha.

IV	SCOPE OF WORK

The composition of the team proposed primarily can be grouped into three broad categories:

- System functionality experts

- Technical team

- Domain experts

The team will be responsible for coordinating with various stakeholders developing, using and monitoring the application. The stakeholder relationship is depicted below:

The broad scope of work proposed for the three categories is as follows:

- System functionality experts

-Attend all user calls.

-Identify nature of problem whether technical, techno functional, administrative or masters related.

-Based on identification, escalate to appropriate team.

-Ensure problem resolution of each ticket raised by end users.

- Based on sound understanding of e-Vittapravaha & continuous interaction with users, identify areas of improvement and initiate change requests.

- Technical team

-Performance tuning and monitoring

-Query building

- Server and database management

- Deployment

-Liason with SDC

-Liason with technical partners

- Domain experts

-Handling and understanding of PFMS, especially related to utilities like DBT purpose mapping etc.

- Coordination & troubleshooting for external integrations

-Liason with PFMS

-Resolving domain issues related to health service delivery

-Coordinating for issues related to planning and financial management of NHM

IV	TEAM COMPOSITION

The proposed team will constitute of 05 resources with the following designations and particulars:

| S No | Designation | Qualification | Experience | Remuneration |
| --- | --- | --- | --- | --- |
| 1 | Technical Consultant Evittapravaha | B. Tech IT/CS/EC | 5 yrs Technical | Rs. 50000 pm |
| 2 | APM Evittapravaha (Domain) | MBA/ PGDHM | 3 yrs Health Program | Rs. 30000 pm |
| 3 | APM Evittapravaha (System) | B. Tech IT or CS/ MCA | 3 Technical | Rs. 30000 pm |
| 4 | Data Manager | B. Tech IT or CS/ MCA | 7 yrs Data Management (Health) | Rs. 40000 pm |
| 5 | Assistant Data Manager | MCA/ PGDCA | 1 yr Technical | Rs. 15000 pm |

V	FINANCIAL PROPOSAL

| Position | Monthly Remuneration | Months | Amount |
| --- | --- | --- | --- |
| Data Manager Evittapravaha | 40000 | 12 | 480000 |
| APM Evittapravaha (System) | 30000 | 12 | 360000 |
| Technical Consultant Evitt | 50000 | 12 | 600000 |
| APM Evittapravaha (Domain) | 30000 | 12 | 360000 |
| Asstt Data Manager Evittapravaha | 15000 | 12 | 48000 |
| Total |  |  | 1848000 |

ACTIVITY 2:   High Risk Pregnancy & Infant Tracking Application (new activity)

I	BACKGROUND

The state of Madhya Pradesh is grappling with high MMR and IMR which are 173 (NITI Aayog report 2016) and 47 respectively. One of the main contributors to MMR and IMR are the high risk cases during the ANC phase which are not timely identified and managed, thus leading to high probability of maternal deaths. A much-required intervention is to ensure timely identification of high risk cases, timely management, tracking their management, ensuring proper and timely referrals to higher level of health facilities and ensuring proper delivery outcomes. Therefore any probable high risk case detected at community level by ANM or ASHA facilitator needs to be referred to higher level of health facility. The two way exchange of information between community and health facility is extremely vital for tracking and management of every high risk case. It is therefore proposed to track the patient movement using a two way communication between the community based android application and the facility based web applications and ensure that the high risk has been managed timely. Evidence has it that the efficient and timely addressal of the high risk cases will substantially contribute to the reduction of MMR and IMR. NHM MP therefore proposes to build an application for tracking High risk mothers and children.

II	Justification

MP is one of the top performing states of ANMOL implementation. The ANMs across the state are trained on the usage of the ANMOL application. However, with the latest reports stating MP as having highest MMR in the state, it is proposed to customise the existing ANMOL for the purpose of timely identification, adequate referral to appropriate level of delivery point and track the management of high-risk ANC. The state level customised version of the ANMOL application, ANMOL MP is the advanced version of ANMOL which is paired with AIS (Anmol Intermediate Server) to provide seamless service from tablet to web both offline and online. Apart from regular ANMOL service, the ANMOL MP is designed to meet the State based requirement where each State can customize the application to cater data element and reports based on their requirements eliminating the need to develop multiple applications.

ANMOL MP is an innovative application for increasing the coverage of Reproductive Child Health, mental health and Immunization interventions by improving performance of public health functionaries through better data management and developing technology-based job aid. ANMOL MP is a mobile and web application being used by ANMs, PHC staff, facilities and health officers at block/district/state level. ANMOL MP digitize ANMs’ multiple register including RCH Register.

In lines of the high-risk pregnant woman tracking application, the state also proposes to leverage technology and improve monitoring of the Home based new born care services. Home Based Newborn Care (HBNC) at community level is being managed to have control on Infant Mortality as mandated by NHM.  HBNC can be bifurcated into normal newborn care and High Risk newborn care wherein a normal newborn health management to be carried on as in current scenario by ASHA on designated mandatory visit days (1,3,7,14,21,28,42 days) but to have better focus and proper accountability, all High Risk new births to be personally visited and managed by the ASHA Facilitator in mandatory 3 fortnightly visits up to 42 (45) days. Therefore, all existing HBNC criterions as well as necessary new elements need to be incorporation into the newly developed ASHA Facilitator App.

By incorporating HBNC visit data into ASHA Facilitator App, ASHA facilitator would be made responsible and accountable for supervising the HBNC visit quality of ASHA work force, data entry of visits done by ASHA into the App and more importantly, ASHA facilitator herself would be directly accountable for the visit, data entry and overall management of all identified High Risk new born cases up to mandatory HBNC monitoring period of 0-42 days.

In order to meet the above objective, it is proposed that features such as due list, matching batching and facility logins be created for Medical officers. The referred cases by ANM gets reflected as due list at the PHC level for the mandatory check-up of every ANC thus ensuring that every woman has had ANC check-up at least once by the Medical officer. Any referrals get referred to the PGMO/Gynaecologis and get reflected in their due list. The MOs at respective levels will be able to see all details entered by the ANM. All entries in turn made by the MO/PGMO/Gynecologist will be reflected in the ANM android application. This close looping of two-way communication will help the state meet the vision of continuity of care and also track missed cases of referrals. The states socio cultural set up many a times dissuades women from seeking timely health care at higher facilities. Pursuing such cases and tracking them with the help of reiterative messages to ANMs and ASHA is the only solution to handle such high-risk cases which are a major contributory factor to the states high MMR and IMR.

The approach of having a single database of RCH MP will lead to avoiding of multiple applications, information overload and duplicate entries. It is envisaged that by developing this central database of MP RCH all other applications will then be integrated with this database. It is an effort to work on the principles of interoperability of multiple applications and making IT systems more compatible to each other whilst also avoiding data discrepancy on same parameters.

IV	Objective:

High Risk Pregnant woman tracking application

- To Upgrade over existing ANMOL/RCH applications with many additional state specific data elements & sub elements.

- To ensure same formats as original ANMOL app to minimize field level user inconvenience and training/re-training efforts.

- To plug gaps of existing application like data syncing issues, additional registers/record maintenance etc.

- To build in additional program specific requirements and all necessary validations for intelligent outputs/reports.

- To Facilitating field workforce with easy to use features of alerts/notifications and tools like EDD calendar, Due lists etc.

- To facilitate early identification of High Risk cases, end-to-end coordination in their tracking & management,

- To build two-way communication between community and facility with proactive reports, due lists, alarms and notifications at both ends.

- Complication based dynamic tagging of facility by ANM at any stage of pregnancy cycle and timely routing of due cases for ANC/Delivery at desired facility. Advance due list availability at respective facility for better coordination

High Risk Infant (HRI)  community level tracking application

- To use an online tracking application for strengthening HBNC services

- To capture information from various sources for identification of new born requiring HBNC

- To effectively identify High Risk Child at community level up to the mandatory HBNC visit period and ensure successful management.

- To fix accountability of ASHA facilitator for high risk HBNC

- To synchronise the child’s health tracking with the place and type of service provider through two applications – ANMOL & ASHA; thus, building synergy to achieve continuum of care.

- To have a single platform for adherence to various guidelines like the IMNCI, FBNC Guidelines and HBNC Guidelines.

V	Deliverables:

High Risk Pregnant woman community level tracking application:

- Timely identification and management of high-risk women during the ANC stage.

- End to end tracking of services being given to High risk pregnant women.

- Mapping batching of all ANC according to service providers to fix accountability.

- Referral Due list for high risk ANC and High-risk delivery according to facility.

- Milestone based payment of JSY and PSY by integration of MP ANMOL/HRP with e-Vittapravah.

High Risk Infant (HRI)  community level tracking application

- Fixed accountability of each child’s HBNC on the ASHA Facilitator.

- Building synergy between child’s movement between various levels of health facilities and home and various service providers.

- To ensure timely referrals of children for any identified high risks.

VI	Funding Proposed:

The funding proposed for HRP and HRI community and facility level are as follows:

| S. No. | Head | Deliverable | Unit | Unit Cost | No. of Units | Total Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Design and Development HRP module | Application Architecture and SRS - Requirement collection from field and development of application architecture, SRS, tooltip and validation document | Prof-days | 10,000 | 50 | 500,000.00 |
|  |  | UI for Android application | Prof-days | 5,000 | 30 | 150,000.00 |
|  |  | Incorporation of additional field in Android application to mark HRP & HRI | Prof-days | 7,000 | 50 | 350,000.00 |
|  |  | Development of EDD module and referral module to track beneficiary | Prof-days | 7,000 | 50 | 350,000.00 |
|  |  | Setting up of user data and role based access to reports | Prof-days | 7,000.00 | 20 | 140,000.00 |
|  |  | Facility Dashboard (with 26 HRP indicator and 100 + permutation and combination) and reports to track beneficiary | Prof-days | 9,000.00 | 100 | 900,000.00 |
|  |  | Analytics(Real time data visualisation, and User based analytics web reports and key performance indicators) | Prof-days | 7,000.00 | 50 | 350,000.00 |
|  |  | Server side implementation to store activity data (Database and API) | Prof-days | 10,000.00 | 30 | 300,000.00 |
|  | Total Cost |  |  |  |  | Rs. 30.4 lakhs |

- Activity :  e-gov Unit (continued activity)

FMR code: 17.7

Activity proposed: Outsourced e gov Unit in NHM

- Justification: The activity was approved in PIP 2018-19 and 2019-20. The unit has been established through outsourcing it to CSC e Governance Services India Limited, which is a Government company under MiETY. The planned activity is budgeted as per actuals including service charges of the company and amounts to INR 85 lakhs for one year.

This team will function as a core team for handling all IT intiatives of NHM and any IT related intervention that may be required by the state. 3 resources are proposed to be continued and the positions are:

| S.No. | Position | Unit cost | CSC charges @30% | Total per month | Total per annum |
| --- | --- | --- | --- | --- | --- |
| 1 | IT Project Coordinator | 1,10,000 | 33,000 | 1,43,000 | 17,16,000 |
| 2 | Sr. Program Manager (IT) | 1,10,000 | 33,000 | 1,43,000 | 17,16,000 |
|  | TOTAL |  |  |  | 34,32,000 |

- Funding proposed:

INR 34.32 lakhs for FY 2020-21. (based on 10% agreed upon yearly increment).

- MAINTENANCE OF EXISTING HARDWARE &SOFTWARE AT STATE LEVEL – (Continued activity)

FMR code: 17.7

Continue Activity:

- Justification: State has multiple web base Applications which have been implemented. The software which is developed by the in-house team needs to undergo security audit and some other applications which have been developed by others needs some customization as per program and state requirement. Additionally, renewal of licenses, anti-virus, firewall etc. also needs to be done on a yearly basis. Additionally, the State needs some cost for Maintenance of existing hardware /software and security audit. With more and more processes getting online, the need to have new hardware may arise. Therefore, some budget has also been parked for the same.

- Funding Proposed:

Maintenance of existing hardware/software and security audit funding are proposed given below.

| Hardware and Software | Unit | Cost |
| --- | --- | --- |
| Maintenance of existing hardware/ software and security audit |  | - Lakh |
| TOTAL |  | 2 lakhs |

- Hardware maintenance at district level (Continue Activity)

FMR code: 17.7

Continue Activity:

- Justification: There are approximately 15 software applications running currently from the district level. Some of them are portals like RCH portal whereas some are process software’s like mpaushadhi, EMMS etc. It is therefore pertinent to provide for hardware maintenance at district level to facilitate any impediments in date entry due to hardware breakdown issues.

b. Funding Proposed:

INR 10,000 per month for 51 districts

Total: INR 5.1 LAKHS

- Activity Proposed:  Support & maintenance of in house developed applications and running application (including integration with other applications) (new activity)

Justification:

The whole life cycle of a software solution might be partitioned into:

1)   Production phase

2)   Maintenance and Support phase

Support and maintenance is an extremely important phase of any application. The monetary implication and importance of this phase has never been understood by the Department, which has led to several applications being developed, yet not serving the purpose of the Program divisions. It is envisaged to make the RCH MP database as the central backbone for NHM MP and ensure culmination of all applications with this backbone. The general perception of software applications in Health Department is confined to the development phase and does not ever include support and maintenance phase. This ignorance of the importance of support and maintenance breeds non acceptance of any financial provisions for this stage. Time and again CRM reports have pointed towards the need to reduce down on multiple applications working in silos by NHM MP.  In order to meet this vision of giving centrality to RCH MP as the main database, many activities will have to be done.

Maintenance is an integral portion of a software’s life-cycle which includes bug fixing as well many other various and complex labor intensive intellectual activities. Maintenance costs, being entirely justified, increase the value and performances of the software itself, and therefore are to be considered as an investment. Bearing this in mind and reiterating the need to undertake a strong support and maintenance phase, it is hereby enlisted the basic activities that this phase has.

In house developed application:

- NHM website

- ASHA

- MW MIS

- CDR

- MDR

- Infra

- Dastak

- PSY

- MSS

Running application

- MP ANMOL /HRP

- E-office

- HRI

In the name existing support & maintenance resource, currently there is only 1 IT Consultant (NHM) and 1 technical support for e-office implementation (outsourced). A proper support and maintenance includes the following tasks, which is imperative for proper functioning of a application. This is an indicative list and may extend beyond as well:

Deliverables:

- Keeping system documentation up-to-date

- Extending existing functions to accommodate new or changing requirements

- Adding new functions to the system

- Finding the source of system failures or problems locating and correcting faults

- Answering questions about the way the system works

- Restructuring design and code components

- Rewriting design and code components

- Deleting design and code components that are no longer useful

- Managing changes to the system as they are made

It is proposed to have an outsourced team for support and maintenance with the following composition:

Funding Proposed:

| S.No. | Profile | Tasks | Amount per month | Unit | Total |
| --- | --- | --- | --- | --- | --- |
| 2 | Developer (.Net) | Support & Maintenance of HRP/HRI etc. | 70,000 | 2 | 16.8 |
| 4 | Network engineer | Maintain intraoffice hardware, Video Conference, network, SWAN implementation in all health facilities etc. | 35,000 | 2 | 8.4 |
|  | TOTAL |  |  |  | 25.2 |

TOTAL PROPOSAL – INR 110.4 Crores